## Sheet1
index	name	latitude	longitude	n_turbines	turbine_power	windfarm_capacity	turbine_installation_start	turbine_installation_end	turbine_installation_vessel	days_per_foundation_lit	days_per_turbine_lit	days_set_lit	Source
1	Utgrunden	56.3439	16.2800	7	1.5	10.5	2000-09-16	2000-10-31	Wind	4.29	6.57	10.86	Lacal-arantegui
2	Middelgrunden	55.6911	12.6689	20	2	40	2000-01-11	2000-12-31	MEB-JB1	3	3	6	Lacal-arantegui
3	Yttre Stengrund	56.1669	16.0211	5	2	10	2001-06-15	2001-07-15	MEB-JB1	11	3.6	14.6	Lacal-arantegui
4	Horns Rev 1	55.5297	7.9061	80	2	160	2002-07-05	2002-08-21	Sea Energy, Sea Power	3.18	2.68	5.85	Lacal-arantegui
5	Rodsand 1	54.5350	11.6672	72	2.3	165.6	2003-09-05	2003-07-27	Sea Energy	5.42	1.1	6.52	Lacal-arantegui
6	Samso	55.7200	10.5831	10	2.3	23	2002-10-12	2003-03-01	Vagant	3.67	3	6.67	Lacal-arantegui
7	North Hoyle	53.3908	-3.4525	30	2	60	2003-03-08	2004-03-15	MEB-JB1, Excalibur, Resolution	5.23	7.33	12.57	Lacal-arantegui
8	Arklow Bank I	52.7889	-5.9489	7	3.6	25.2	2003-01-09	2003-05-10	Sea Jack	6.57	4.86	11.43	Lacal-arantegui
9	Scroby Sands	52.6450	1.7869	30	2	60	2004-03-25	2004-01-06	Sea Energy, Excalibur	2.6	2.07	4.67	Lacal-arantegui
10	Kentish Flats	51.4600	1.0900	30	3	90	2005-01-05	2005-08-22	Sea Energy	1.97	3.8	5.77	Lacal-arantegui
11	Barrow	53.9833	-3.2833	30	3	90	2005-01-12	2006-04-30	Resolution	5.97	5	10.97	Lacal-arantegui
12	Lillgrund	55.5111	12.7789	48	2.3	110.4	2007-03-08	2007-10-16	Sea Power	8.56	1.54	10.1	Lacal-arantegui
13	OWEZ			36	3	108	2006-02-06	2006-08-26	Sea Energy	3.25	2.39	5.64	Lacal-arantegui
14	Burbo Bank	53.4881	-3.1869	25	3.6	90	2007-05-20	2007-06-29	Sea Jack	2.24	1.6	3.84	Lacal-arantegui
15	Beatrice pilot	58.0981	-3.0781	2	5	10	2007-01-07	2007-07-31	Rambiz	8.5	30	38.5	Lacal-arantegui
16	Prinses Amalia	52.5881	4.2231	60	2	120	2007-05-16	2007-11-16	Sea Jack, Sea Energy	3.03	6.13	9.17	Lacal-arantegui
17	Lynn & Inner Dowsing	53.1361	0.4581	54	3.6	194.4	2008-03-15	2008-07-15	Resolution	4.33	2.26	6.59	Lacal-arantegui
18	Robin Rigg	54.7500	-3.7167	60	3	180	2008-04-11	2009-08-31	Sea Worker, Sea Energy	4.18	5	9.18	Lacal-arantegui
19	Thornton Bank I	51.5400	2.9400	6	5	30	2008-07-16	2008-09-20	Buzzard	7	11	18	Lacal-arantegui
20	Rhyl Flats	53.3878	-3.6708	25	3.6	90	2009-03-04	2009-10-10	Lisa A	3.96	7.6	11.56	Lacal-arantegui
21	Horns Rev 2	55.5297	7.9061	91	2.3	209.3	2009-03-15	2009-11-14	Sea Power	1.61	2.71	4.32	Lacal-arantegui
22	Gunﬂeet Sands I & II	51.7300	1.2289	48	3.6	172.8	2009-03-24	2010-01-31	Sea Worker, KS Titan	2.39	4.58	6.97	Lacal-arantegui
23	Thanet	51.4250	1.6175	100	3	300	2009-09-12	2010-06-24	Resolution	5.47	1.97	7.44	Lacal-arantegui
24	Rodsand II	54.5350	11.6672	90	2.3	207	2009-03-20	2010-07-15	Sea Power	3.37	5.36	8.73	Lacal-arantegui
25	Alpha Ventus (T)	54.0083	6.5983	6	5	30	2009-02-06	2009-09-16	Taklift 4,	7.5	17.67	25.17	Lacal-arantegui
26	Alpha Ventus (J)	54.0083	6.5983	6	5	30	2009-09-25	2009-11-16	Thialf, Buzzad	14.83	8.67	23.5	Lacal-arantegui
27	Sprogo	55.3431	10.9581	7	3	21	2009-10-16	2009-05-11	Sea Energy	2	2.86	4.86	Lacal-arantegui
28	Belwind	51.6700	2.8019	55	3	165	2010-03-26	2010-09-16	JB114, JB115	5.38	3.22	8.59	Lacal-arantegui
29	Greater Gabbard	51.8800	1.9400	140	3.6	504	2010-09-05	2012-03-21	Leviathan, Sea Jack, Kraken	3.69	2.78	6.47	Lacal-arantegui
30	Walney I	54.0439	-3.5219	51	3.6	183.6	2010-10-07	2011-01-24	Kraken, Sea Worker	2.69	4.76	7.45	Lacal-arantegui
31	BARD Oﬀshore I	54.3583	5.9750	80	5	400	2010-02-12	2013-01-08	Brave Tern, Thor, JB115, JB117	14.09	26.63	40.71	Lacal-arantegui
32	EnBW Baltic 1	54.6089	12.6511	21	2.3	48.3	2010-07-27	2010-02-09	Sea Power	3	1.76	4.76	Lacal-arantegui
33	Sheringham Shoal	53.1350	1.1469	88	3.6	316.8	2011-08-06	2012-10-07	Endeavour; Leviathan	3.18	6.89	10.06	Lacal-arantegui
34	Ormonde	54.1000	-3.4000	30	5.075	152.25	2011-03-17	2011-01-08	Sea Jack	4.61	4.57	9.18	Lacal-arantegui
35	London Array	51.6333	1.5500	175	3.6	630	2012-01-27	2012-12-29	Discovery, Sea Worker, Sea Jack	4.31	3.26	7.57	Lacal-arantegui
36	Lincs	53.1833	0.4833	75	3.6	270	2012-04-07	2013-03-31	Resolution	5.93	3.61	9.55	Lacal-arantegui
37	Thornton Bank II	51.5400	2.9400	30	6.15	184.5	2012-03-18	2012-07-27	Neptune, Vagant	7.36	8.8	16.16	Lacal-arantegui
38	Walney II	54.0439	-3.5219	51	3.6	183.6	2011-05-15	2011-09-26	Leviathan, Kraken	3.94	4.25	8.2	Lacal-arantegui
39	Trianel Borkum 1	54.0461	6.4569	40	5	200	2013-07-24	2014-01-06	Adventure	8.23	7.8	16.03	Lacal-arantegui
40	Anholt	56.6031	11.2089	111	3.6	399.6	2012-08-31	2013-05-19	Sea Power, Sea Worker, Sea Installer, Sea Jack	2.81	4.37	7.18	Lacal-arantegui
41	Teesside	54.6500	-1.1000	27	2.3	62.1	2013-06-01	2013-02-06	Adventure	8.96	5.52	14.48	Lacal-arantegui
42	Thornton Bank III	51.5400	2.9400	18	6.15	110.7	2013-11-03	2013-03-07	Goliath, Vagant	6.52	12.78	19.3	Lacal-arantegui
43	Borkum Riﬀgat	53.6900	6.4800	30	3.775	113.25	2013-04-25	2013-07-18	Bold Tern	2.97	2.83	5.8	Lacal-arantegui
44	Gwynt y Mor	53.4500	-3.5833	160	3.6	576	2013-04-29	2014-06-28	Sea Jack, Sea Worker	5.02	5.02	10.04	Lacal-arantegui
45	Karehamn	56.9839	17.0219	16	3	48	2013-01-05	2013-07-25	Discovery	4	5.31	9.31	Lacal-arantegui
46	Meerwind	54.3833	7.6833	80	3.6	288	2013-07-17	2014-03-04	Zaratan, Leviathan	6.36	6.49	12.85	Lacal-arantegui
47	Global Tech I	54.5000	6.3583	80	5	400	2013-08-22	2014-08-29	Thor, Brave Tern, Bold Tern, Vole au vent, Innovation	6.14	9.3	15.44	Lacal-arantegui
48	Gunﬂeet Sands III	51.7300	1.2289	2	6	12	2013-03-01	2013-01-16	Sea Installer	6	6.5	12.5	Lacal-arantegui
49	Nordsee Ost	54.4333	7.6833	48	6.15	295.2	2014-05-19	2014-12-27	Victoria Mathias, Friedrich Ernestine	9.24	7.69	16.93	Lacal-arantegui
50	Belwind Haliade prot.			1	6	6	2013-07-10	2013-11-17	Bold Tern	0	44	44	Lacal-arantegui
51	Dan Tysk	55.1500	7.1750	80	3.6	288	2014-03-28	2014-08-27	Paciﬁc Osprey	3.86	1.9	5.76	Lacal-arantegui
52	Northwind	51.6167	2.9000	72	3	216	2013-07-20	2014-03-29	Resolution, Neptune	2.07	3.29	5.36	Lacal-arantegui
53	West of Duddon Sands	53.9839	-3.4639	108	3.6	388.8	2013-09-25	2014-03-06	Sea Installer	2.16	2.32	4.48	Lacal-arantegui
55	Humber Gateway	53.6439	0.2931	73	3	219	2014-07-20	2015-04-23	Resolution	3.45	3.79	7.25	Lacal-arantegui
56	EnBW Baltic II (MP)	54.9731	13.1781	39	3.6	140.4			Vole au vent	5.26	3.81	9.07	Lacal-arantegui
57	Amrumbank West	54.5000	7.8000	80	3.775	302	2015-05-02	2015-08-09	Adventure	4.58	2.69	7.26	Lacal-arantegui
58	Borkum Riﬀgrund 1	53.9667	6.5500	78	4	312	2014-10-25	2015-05-22	Sea Installer	2.48	2.68	5.16	Lacal-arantegui
59	Westermost Rough	53.8050	0.1489	35	6	210	2014-06-08	2015-03-27	Sea Challenger	2.66	6.66	9.31	Lacal-arantegui
60	Butendiek	55.1074	7.7769	80	3.6	288	2014-12-09	2015-12-06	Bold Tern	2.79	3.41	6.2	Lacal-arantegui
61	Luchterduinen	52.4050	4.1619	43	3	129	2015-06-04	2015-10-06	Aeolus	1.84	1.51	3.35	Lacal-arantegui
62	Westermeerwind	52.7389	5.5861	48	3	144	2015-06-09	2016-01-03	De Schelde	1.44	3.69	5.13	Lacal-arantegui
63	Gode Wind I & II	54.0667	7.0333	97	6	582	2015-05-08	2016-05-19	Sea Challenger	1.63	2.97	4.6	Lacal-arantegui
64	Kentish Flats Extension	51.4600	1.0900	15	3.3	49.5	2015-06-14	2015-10-08	Neptune	1.47	3.8	5.27	Lacal-arantegui
65	Gemini	54.0333	5.9333	150	4	600	2016-12-02	2016-08-23	Aeolus, Paciﬁc Osprey	1.43	2.52	3.95	Lacal-arantegui
66	Sandbank	55.1833	6.8500	72	4	288	2016-07-25	2017-01-21	Adventure	2.64	2.5	5.14	Lacal-arantegui
67	Nordsee One	53.9667	6.8000	54	6.15	332.1	2017-03-03	2017-09-22	Victoria Matthias	2.33	3.76	6.09	Lacal-arantegui
68	Rampion	50.6700	-0.2769	116	3.45	400.2	2017-07-03	2017-09-20	Discovery, Adventure	2.86	2.55	5.41	Lacal-arantegui
69	Veja Mate	54.3169	5.8708	67	6	402	2017-07-01	2017-05-30	Bold Tern, Scylla	3.91	3.34	7.25	Lacal-arantegui
70	Dudgeon	53.2667	1.3833	67	6	402	2017-05-01	2017-05-09	Sea Challenger	1.84	3.63	5.46	Lacal-arantegui
71	Wikinger	54.8339	14.0681	70	5	350	2017-01-16	2017-10-22	Brave Tern	7.04	3.99	11.03	Lacal-arantegui
72	Nordergrunde	53.8333	8.1667	18	6.15	110.7	2016-12-08	2016-12-21	Victoria Matthias	4.39	7.28	11.67	Lacal-arantegui
73	Nobelwind	51.6600	2.8200	50	3.3	165	2016-10-25	2017-03-04	Vole au vent	2.49	3.2	5.69	Lacal-arantegui
74	Burbo Bank Extension	53.4831	-3.2731	32	8	256	2016-06-09	2016-12-14	Sea Challenger	1.66	3.96	5.62	Lacal-arantegui	Fehler? Laut daten war die Sea Challenger das installationsschiff fuer die turbinen	https://www.windkraft-journal.de/tag/sea-challenger
75	Race Bank	53.2758	0.8408	91	6.3	573.3	2017-04-30	2017-12-18	Sea Challenger	2.23	2.55	4.78	Lacal-arantegui
76	Galloper	51.8919	2.0339	56	6.3	352.8	2017-05-14	2017-12-22	Paciﬁc Orca, Bold Tern	1.64	5.41	7.05	Lacal-arantegui
77	Walney 3	54.0869	-3.7369	40	8.25	330	2017-03-08	2017-10-11	Scylla	2.51	2.48	4.98	Lacal-arantegui
78	Walney 4	54.0869	-3.7369	47	7	329	2017-12-28		Scylla	2.51			Lacal-arantegui
79	Ajos	65.6511	24.5306	8	3.3	26.4	2017-06-18	2017-03-07	Vole au Vent	2.7	1.5	4.2	Lacal-arantegui
80	Tahkoluoto	61.6281	21.3531	10	4.2	42	2017-06-18	2017-03-07	Vole au Vent	2.4	1.5	3.9	Lacal-arantegui
81	Blyth Demonstration	55.1361	-1.4900	5	8.3	41.5	2017-09-13	2017-09-28	Vole au Vent	8	3	11	Lacal-arantegui
82	Hywind Scotland			5	6	30	2017-07-19	2017-08-16	Tugs		1.87	1.87	Lacal-arantegui
83	Rentel	51.5911	2.9439	42	7.35	308.7			Apollo	1.33			Lacal-arantegui
84	Arkona	54.7819	14.1211	60	6.417	385			Sea Challenger	2.4			Lacal-arantegui
85	Nissum Bredning	56.6689	8.2450	4	7	28	2017-11-13	2018-05-01	Crane on a barge	14.75	13.25	28	Lacal-arantegui
86	Aberdeen (EOWDC)	57.2250	-1.9931	11	8.4	93.2	2018-06-04		Paciﬁc Orca				Lacal-arantegui
87	Albatros	54.5000	6.4000	16	7	112			Blue Tern, Brave Tern				https://www.enbw.com/renewable-energy/wind-energy/our-offshore-wind-farms/hohe-see/construction-diary.html
88	Block Island	41.1150	-71.5211	5	6	30			Brave Tern				https://en.wikipedia.org/wiki/Block_Island_Wind_Farm
89	Borkum Riffgrund 2	53.9667	6.5500	56	8	448			Bold Tern				https://windcarrier.com/media/0bvj2zc3/transport-and-installation-track-record_10062021.pdf
90	Borssele I/II	51.7450	3.0611	94	8	752			Sea Challenger				https://www.offshore-energy.biz/sea-challenger-loading-first-borssele-12-turbine-components-in-esbjerg/	https://www.offshorewind.biz/2020/04/13/first-borssele-12-wind-turbine-stands/
91	Coastal Virginia Beach	36.9069	-75.4911	2	6	12			Vole au Vent				https://www.offshorewind.biz/2020/05/21/vole-au-vent-sets-off-to-begin-cvow-construction/
92	Deutsche Bucht	54.3050	5.7989	31	8.4	260.4			Aeolus				https://www.vanoord.com/en/updates/aeolus-completes-turbine-installation-deutsche-bucht-offshore-wind-farm/
93	East Anglia One	52.2339	2.4778	102	7	714			Sea Challenger				https://www.windkraft-journal.de/tag/sea-challenger
94	EnBW Hohe See	53.6900	6.4800	71	7	497			Brave Tern, Blue Tern				https://www.windkraft-journal.de/tag/brave-tern
95	Horns Rev 3	55.6944	7.6565	49	8.3	406.7			Brave Tern				https://www.offshorewind.biz/2018/07/20/first-horns-rev-3-wind-turbine-rises/
96	Hornsea	53.8850	1.7911	174	7	1218			Bold Tern, Sea Challenger				https://www.windkraft-journal.de/tag/sea-challenger
97	Kriegers Flak	55.0261	12.9389	72	8	576			Vole au Vent				https://www.esgian.com/articles/vole-au-vent-completes-installation-of-turbines-on-kriegers-flak-owf/1910
98	Merkur	54.0333	6.5500	66	6	396			Blue Tern				https://windcarrier.com/track-record/case-studies/moray-east/
99	Moray East	58.1881	-2.7200	100	9.5	950			Blue Tern, Bold Tern				https://windcarrier.com/track-record/case-studies/moray-east/
100	Norther	51.5269	3.0139	44	8.4	369.6			Aeolus				https://www.offshorewind.biz/2018/08/07/first-norther-steel-in-water/	https://www.offshorewind.biz/2019/04/29/all-norther-turbines-stand-tall/
101	Northwester 2	51.6861	2.7569	23	9.5	218.5			Vole au Vent				https://de.wikipedia.org/wiki/Offshore-Windpark_Northwester_2
102	Saint Brieuc	48.8531	-2.5361	62	8	496
103	Trianel Borkum 2	54.0461	6.4569	32	6.33	202.56			Blue Tern
104	Yunlin	23.5889	120.0269	80	8	640			Brave Tern